## Text
File Name | Page Number | Heading | Sub Heading | Description
UNESCO_State_of_Conservation_Report_The_Sundarbans_2025.pdf | 11 | 2.7.11 Ecological Monitoring of the Sundarbans | Ecological monitoring activities are being conducted in accordance with the approved Methodological | 2.7.11 Ecological Monitoring of the Sundarbans Ecological monitoring activities are being conducted in accordance with the approved Methodological Framework of Ecological Monitoring of the Sundarbans. Expert teams are systematically carrying out field surveys to gather data on both biotic and abiotic indicators, encompassing vegetation, wildlife, as well as air, soil, and water parameters. The primary objective of this monitoring is to establish a comprehensive baseline dataset reflecting the ecological status of the Sundarbans and to develop an Integrated Ecological Monitoring System for long-term, periodic assessment to inform management and conservation actions. The assignment is progressing according to schedule and is anticipated to be completed by mid-2026. 2.7.12 Assessment of Aquatic Resources of the Sundarbans The Draft Assessment of Aquatic Resources of the Sundarbans has been prepared in October 2025 as part of the Protection of Sundarbans Mangrove Forests Project (PSMFP). This report provides detailed reports on aquatic resource management, fish biodiversity monitoring, shellfish (mollusks and crustacean) biodiversity, fisheries stock assessment, DNA taxonomy analysis, non-piscine aquatic species, mangrove ecology study, climate change and fisheries management practices and provides recommendations for their management. 2.7.13 National Forest Inventory Bangladesh Forest Department (BFD) is implementing bio-physical and socio-economic survey under the National Forest Inventory including Sundarbans. The analysis of these data will provide update information on the tree resource of Sundarbans as well as the degree of dependency of local community on forest resources by December 2025. 2.7.14 Sustainable Development Goal (SDG) Sustainable Development Goal (SDG) 6, Which aims to ‘‘ensure availability and sustainable management of water and sanitation for all,” highlights the critical importance of integrated water resources management (IWRM). Bangladesh Water
UNESCO_State_of_Conservation_Report_The_Sundarbans_2025.pdf | 2 | 1. Executive Summary of the report | Bangladesh, a South Asian country rich in biodiversity, is committed to preserving and conserving its | 1. Executive Summary of the report Bangladesh, a South Asian country rich in biodiversity, is committed to preserving and conserving its natural resources. Although the country contributes very little to global carbon emissions, it is among the most climate-vulnerable nations in the world. Climate change poses significant risks to both the sustainability of conservation efforts in the Sundarbans and the country’s broader sustainable development goals. Despite facing climate-induced threats-such as sea-level rise leading to salinity intrusion in the Sundarbans, more frequent cyclones, droughts, and other extreme climatic events that place immense pressure on conservation initiatives-Bangladesh continues to invest substantial resources in protecting its environment, including the Sundarbans. Bangladesh takes great pride in being home to the Sundarbans-the world’s largest mangrove forest and in the UNESCO recognition of its three wildlife sanctuaries as World Heritage Sites in 1997. The forest covers approximately 6,017 sq. km within Bangladesh and is renowned as a global biodiversity hotspot, supporting 270 species of birds, 35 species of reptiles, and 42 species of mammals. It also provides critical habitat for threatened and endangered species such as the estuarine crocodile, Indian python, and Bengal tiger. According to the Draft National Forest Inventory (NFI) report 2024, the Sundarbans carbon stock increased from 139 million tons in 2019 to 143.80 million tons in 2024. The forest experienced almost no loss of cover between 2001 and 2025, and the long-standing moratorium on tree felling has been extended to 2030. In 2017, the extent of Protected Areas was expanded to 53.52% of the Sundarbans, up from the previous 23%. To safeguard forest resources and strengthen law enforcement, SMART (Spatial Monitoring and Reporting Tools) and drone-assisted patrols have been deployed since 2015. Six Dolphin Wildlife Sanctuaries have also been declared within and around the Sun
UNESCO_State_of_Conservation_Report_The_Sundarbans_2025.pdf | 3 | The State Party reaffirms its strong commitment to safeguarding the Outstanding Universal Value (OUV) | of the property while implementing forward-looking development plans for the region in the decades | The State Party reaffirms its strong commitment to safeguarding the Outstanding Universal Value (OUV) of the property while implementing forward-looking development plans for the region in the decades ahead. The diverse interventions undertaken clearly reflect this dedication and demonstrate the extent to which the State Party is prepared to integrate nature conservation into its national development agenda. 2. Response to the Decision of the World Heritage Committee (Decision: 45COM 7B.14) 2.1. Decision no. 2 Recalling Decisions 38 COM 78.64, 41 COM 78.25, 43 COM 78.3 and 44 COM 78.91 adopted at its 38th (Doha, 2014), 41st (Kraków, 2017), 43rd (Baku, 2019) and extended 44th (Fuzhou/online, 2021) sessions respectively, Response A comprehensive response on the decisions 41 COM 7B.25, 43 COM 7B.3 and 44 COM 7B.91 has already been sent to the WHC on 29.11.2018, 30.01.2020 and 30.01.2022 respectively. 2.2 Decision no. 3 Welcomes the State Party's continued efforts towards enhancing the protection of the property and the progress in implementing the recommendations of the 2019 joint World Heritage Centre/IUCN Reactive Monitoring mission, undertaking. effective conservation measures through planned forestation and requests to continue to implement the mission recommendations as agreed by the State Party and previous Committee decisions, Response The state party remains fully committed to sustaining and strengthening effective conservation measures, including planned forestation initiative and reaffirms its dedication to carrying forward all mission recommendations and previous committee decisions as agreed. 2.3 Decision no. 4 Appreciates the national measures taken by the State Party on the Maitree Super Thermal Power Plant (MSTP) to avoid impacts on the Outstanding Universal Value (OUV), in accordance with the Environmental Management Plan, and further appreciates the decision of the State Party to revise the Power Systern Master Plan (PSMP) to replace the second unit of
UNESCO_State_of_Conservation_Report_The_Sundarbans_2025.pdf | 9 | 2.7.5 | Initiatives to mitigate Human-Wildlife Conflict through compensation | 2.7.5 Initiatives to mitigate Human-Wildlife Conflict through compensation To resolve the issue of Human-Wildlife Conflict, the Government enacted Wildlife Victims Compensation Rules in 2021. According to these rules in case of death of a person attacked by a wildlife the victim’s family will get compensation of BDT 3,00,000 and in case of serious injury BDT 1,00,000, which was earlier BDT 1,00,000 and BDT 50,000 respectively. So far, compensation has been provided to 27 people injured in tiger attacks and the families of 75 people killed, while compensation has been provided to 3 people injured in crocodile attacks and the families of 5 people killed. 2.7.6 Initiatives for rewarding the informer about the wildlife’ poachers/smugglers The Bangladesh Government enacted Rules declaring reward package for the informers on Wildlife crimes in 2020. According to these rules, if anyone provides any crime information related to poaching, hunting, trapping, smuggling or other crime, the informer will be rewarded. This helps to prevent wildlife crimes in Sundarbans. So far, a total of BDT 5,25,000 has been rewarded to 52 informants for providing information related to wildlife crimes, as per the rules. 2.7.7 Initiatives for Tiger Conservation • Second generation Bangladesh Tiger Action Plan (2018-27) has been approved by the Government. The first generation BTAP was for the period 2009-2017. It provides a vision, goals and objectives to guide an integrated and focused tiger conservation program. • National Tiger Recovery Program (2017-22) was developed and which is currently under process of updating for the period 2023 to 2034. • The results of the tiger census, conducted through camera trapping, were announced in 2024. The number of tigers in the Sundarbans has been found 125, which was 114 in the last census in 2018. • Research on Parasitic infection and other communicable diseases, with their causal agents and extent in Sundarbans tigers is ongoing under Sundarbans Tiger
UNESCO_State_of_Conservation_Report_The_Sundarbans_2025.pdf | 12 | 2.7.15 Environmental Cooperation and Management | MPA continues to work under the framework of the Strategic Environmental Management Plan (SEMP) | 2.7.15 Environmental Cooperation and Management MPA continues to work under the framework of the Strategic Environmental Management Plan (SEMP) Bangladesh, a national initiative designed to address environmental challenges, conserve natural resources, and promote sustainable development in and around the Sundarbans region. MPA's environmental actions are aligned with the recommendations of the World Heritage Committee, ensuring integrated management and environmentally responsible port operations. 2.7.16 Jurisdiction and Coordination The establishment or control of large-scale industrial development in the region lies outside MPA's jurisdiction. Nevertheless, any future port-related initiatives will be undertaken in close cooperation with the National SEMP and relevant government agencies to ensure full compliance with UNESCO's conservation standards and to avoid any adverse impact on the Outstanding Universal Value (OUV) of the property. 2.7.17 No Adverse Constructions or Activities MPA confirms that it has not undertaken any major restorations, dredging, or construction projects that could affect the OUV, authenticity, or integrity of the Sundarbans. Port maintenance activities are carefully monitored under national environmental laws and international best practices. 2.7.18 Current Status The Sundarbans (Bangladesh) is not inscribed on the List of World Heritage in Danger. MPA acknowledges and supports national efforts to maintain this status through continuous monitoring, compliance and cooperation with UNESCO and IUCN guidelines. Mongla Port Authority reaffirms its strong commitment to ensuring that all port operations and, developmental activities are consistent with UNESCO World Heritage conservation principles. MPA maintains close coordination with the Ministry of Environment, Forest and Climate Change (MoEFCC), the Department of Environment (DoE), and National SEMP Bangladesh to support the long-term protection and sustainable management of the Sundarbans W
UNESCO_State_of_Conservation_Report_The_Sundarbans_2025.pdf | 13 | 2.8 Decision no. 9 | Takes note of the ongoing preparation of the new 2025-2035 Integrated Resource Management Plan | 2.8 Decision no. 9 Takes note of the ongoing preparation of the new 2025-2035 Integrated Resource Management Plan (IRMP) for the Sundarbans and requests furthermore the State Party to continue consultations with the communities; Response The Draft Integrated Resources Management Plan (IRMP) for the Sundarbans 2025–2035 was submitted to the Bangladesh Forest Department (BFD) in October 2025 as part of the Protection of Sundarbans Mangrove Forests Project (PSMFP). This report incorporates comprehensive inputs, suggestions, and recommendations from forest-dependent livelihood groups, local government representatives, Co- management Committees, academicians, and BFD officials. The draft outlines 13 distinct management programs, each featuring detailed prescriptions and strategic actions designed to facilitate the sustainable management of the Sundarbans Reserved Forest (SRF). Following submission, the BFD thoroughly reviewed the draft and provided comments and recommendations. These are presently being addressed by the Expert Team. The finalized IRMP 2025– 2035 is scheduled for completion by December 2025, pending outcomes of the national validation workshop. 3. Other current conservation issues identified by the State(s) Party(ies) which may have an impact on the property's Outstanding Universal Value At present, no significant conservation issues have been identified. However, several research initiatives are currently underway, including ecological monitoring; the Assessment of Aquatic Resources of the Sundarbans; the updating of the IRMP; studies on parasitic infections and other communicable diseases affecting tigers; and the Monitoring of 27 Crime-Prone Hotspots for Tiger and Deer Poaching in the Sundarbans through Camera Trapping. These activities are being conducted under the Sundarban Protection Project and the Tiger Conservation Project, and their findings will be finalized soon. Should any major conservation concern emerge from these studies-particularly one
UNESCO_State_of_Conservation_Report_The_Sundarbans_2025.pdf | 7 | In 1996, 3(three) wildlife sanctuaries (Sundarban East, West and South) were declared with an area of | about 1,39,699.49 hectares for biodiversity conservation and maintain undisturbed breeding ground for | In 1996, 3(three) wildlife sanctuaries (Sundarban East, West and South) were declared with an area of about 1,39,699.49 hectares for biodiversity conservation and maintain undisturbed breeding ground for wildlife which are also the World Heritage Site (WHS). The area of these 3(three) Protected Areas has been increased to 3,17,950.08 ha in 2017. Now, the total area of Protected Areas covers about 53.52% area of the Sundarbans. Collection/extraction or harvesting of all kinds of resources is strictly prohibited from the Protected Areas. 2.7.3 Spatial Monitoring and Reporting Tools (SMART) Patrolling in the Sundarbans: SMART (Spatial Monitoring & Reporting Tools) based monitoring system is being implemented in the Sundarbans since 2015. This monitoring system has become very much helpful to monitor and protect the resources of the Sundarbans. A total of 3747 suspects were arrested from January 2018 to October 2025. During patrols, 2257 watercrafts, 2459 fish and crab traps, 395 tree cutting tools were seized, and 99 cases of fishing with poison were recorded. Drone based monitoring system has also been adopted in the SMART patrolling. During this period, 48,530 terrestrial mammals, 11,770 aquatic mammals, 6,128 reptiles and 21,439 birds were observed. 23 different types of wildlife were observed during SMART patrolling in the Sundarbans. 2.7.4 Initiatives for Dolphin Conservation Waterways of the Sundarbans mangrove forest, supports the Vulnerable Ganges River dolphin (Platanista gangetica) and Near Threatened Irrawaddy dolphin (Orcaella brevirostris). For effective conservation and management, based on scientific study and survey 6(six) dolphin sanctuaries (Dhangmari, Chandpai, Dudhmkhi, Shibsha, Bhodra and Pankhali) covering 4497.0 hectares have been established in and adjacent areas of the Sundarbans. 70 Members are working under 7(seven) Dolphin Conservation Teams (DCT) in the field along with Bangladesh Forest Department staff and Co- Management Committee to awar
UNESCO_State_of_Conservation_Report_The_Sundarbans_2025.pdf | 4 | (IPEMP 2023), the Nationality Determined Contribution (NDC) and the national priority of safeguarding | the Outstanding Universal Value (OUV) of the surrounding area. Subsequent policy decisions regarding | (IPEMP 2023), the Nationality Determined Contribution (NDC) and the national priority of safeguarding the Outstanding Universal Value (OUV) of the surrounding area. Subsequent policy decisions regarding the future of block B will be based on the feasibility study's recommendations, taking into consideration environment safeguards, system planning requirements and the government strategic direction towards cleaner and more sustainable energy development. 2.4 Decision no. 5 Notes with appreciation the completion of the Strategic Environmental Assessment (SEA) and the Strategic Environmental Management Plan (SEMP) for the South-West region of Bangladesh in 2021 and submission to the World Heritage Centre in 2023, and further notes the findings of the SEA that the scale of potential degradation of the OUV of the property through proposed development scenarios remains unknown, and also requests the State Party to a) continue to implement the SEMP in order to avoid direct, indirect and cumulative impacts from developments in the South-West region over the next twenty years that are identified in the SEA, Response The State Party appreciates this guidance and reaffirms its strong commitment to the continued implementation of the Strategic Environmental Management Plan (SEMP). We fully recognize the importance of addressing the direct, indirect, and cumulative impacts of development in the South-West region over the coming decades, as identified in the Strategic Environmental Assessment (SEA). The State Party will continue to apply the SEMP as a key instrument to ensure sustainable development, safeguard ecological integrity, and uphold its obligations to protect the Outstanding Universal Value of the property. The Government of Bangladesh has promulgated the Environment Conservation Rules (ECR) 2023, replacing the ECR 1997. It has also, for the first time, introduced the Air Pollution Control Rules 2022 and updated the Noise Pollution (Control) Rules 2025. Industries in th

## Graph
File Name | Page Number | Graph Image | Graph Image Caption | Description