## Text
File Name | Page Number | Heading | Sub Heading | Description
FAO_6086-f.pdf | 5 | 1 INTRODUCTION | Quality assurance and quality control are fundamental for the Bangladesh Forest Inventory (BFI) to reach its | 1 INTRODUCTION Quality assurance and quality control are fundamental for the Bangladesh Forest Inventory (BFI) to reach its objectives and for Bangladesh to fully benefits from this inventory and guide proper decisions in tree and forest management and conservation at all levels. Quality assurance (QA) encompasses all activities performed to ensure that the field data achieve the desired quality (USDA, 2012). It focuses on identification and documentation of operations and procedures that affect data quality. Quality control (QC) is a system of routine of technical activities to measure and control the quality of the inventory to maintain data quality within an acceptable range. It ensures the data integrity, correctness and completeness, identifies and addresses errors and omissions, and documents and archives inventory material and record all QC activities. QA/QC activities include a planned system of review procedures conducted both by BFI personnel and by personnel which is not directly involved in the BFI development process (external review). The review provides valuable feedback for the inventory. Major elements of QA/QC are illustrated in Figure 1. QA/QC plan is prepared in order to provide a framework for each activity to be completed (Tulyasuwan, Federici, M., Jonckheere, & Henry, 2011). 1.1 PURPOSE AND SCOPE OF THIS MANUAL This report provides information about the:  Organizational structure, to identify the roles and responsibilities for QA/QC activities (chapter 2); and  General inventory QC/QA procedures, i.e. a description of the QC/QA routines checks that will be implemented across all phases of inventory (chapter 3). Inform about the location of plots to be measured BFI Unit Field Team Frequent submission of data Inform about the Inform about the subplots to be result of hot & Supervise, provide checked & cold check authorization provide compiled letter & legal Regularly inform field forms support about the progresses Inform about team performance
FAO_6086-f.pdf | 6 | 1.2 THE QUALITY OF THE DATA | Improvement of the quality of the data can be done at different stages of the inventory: (1) before field work, (2) | 1.2 THE QUALITY OF THE DATA Improvement of the quality of the data can be done at different stages of the inventory: (1) before field work, (2) during field work (including hot checks & cold checks) and (3) after field work. The goal of the QA is to ensure that data attained meets the minimum specified standards. Data collected for QA purposes can also provide the feedback that is necessary to develop realistic measurement quality objectives (MQOs), revise data collection methods to reduce errors, improve training, and aid in the interpretation of results. The main criteria used to interpret the level of data quality are (Michael. E. Schomaker et al., 2007): 1. Precision—the ability of a method to reproduce the same value 2. Accuracy—the ability of a method to yield the “true” value 3. Completeness—the amount of valid, usable data produced by a method 4. Comparability—the ability to combine data collected by different methods, in different locations, and by different data collectors. The effectiveness of the QA will contribute to prevent data quality problems, assessment and appraisal, and correction. 1.3 MEASUREMENT QUALITY OBJECTIVES Each variable has a Measurement Quality Objectives (MQOs) composed by 2 parts: (1) a tolerance, and (2) a compliance standard. (1) is the maximum measurement error accepted, expressed in percentage on the real value, and (2) is the maximum number of errors accepted, expressed in percentage on the number of measured individuals. E.g. For variable “DBH” (diameter at breast height): 1. Tolerance = ±10% In this case, for example, for a tree of 50 cm of diameter the tolerance will be of ± 5 cm (which is the 10% of 50) and all measurements bigger than 55cm or smaller than 45cm have to be considered as errors. 2. Compliance standard = at least 90% of measurements That is, for example, if 50 trees have to be measured, at least 45 have to be measured correctly (i.e. within the tolerance range). If less than 45 trees have been measured correctl
FAO_6086-f.pdf | 7 | 2 ORGANIZATIONAL STRUCTURE | 2.1 THE BFI UNIT | 2 ORGANIZATIONAL STRUCTURE 2.1 THE BFI UNIT The BFI unit in the Forest Department is responsible for coordinating and executing all BFI field activities, and finally to collate, validate, and disseminate the results. The BFI unit provides the logistical support and supervision to the field (Forest Biophysical and Socio-Economic aspects) personnel and is responsible for monitoring, supervising, and backstopping the fieldwork. The BFI unit should provide field report checks, in order to ensure timely completion for field work, data quality and homogeneity among field teams. The BFI team controls and coordinates the data collection process, the transfer of field forms, and the validation of field forms in preparation for data entry. 2.2 THE SUPERVISORS Field administration forest zones of Bangladesh are divided into 9 forest circles, each of them headed by a Conservator of Forests. Each of them except Conservator of Forests, Wildlife and Nature Conservation Circle will serve as a Supervisor for the national forest inventory purpose. Supervisors will be responsible for coordinating and ensuring the execution all BFI field activities. Supervisor will coordinate all field teams’ activities and QA/QC field activities. The supervisor should provide immediate response and support to field teams if an emergency occurs. Supervisor will convene meeting with field teams and QA/QC teams to remove any errors he comes across during his visit. Supervisor will send a monthly report to DCCF, Planning Wing with copy to CCF abound his observation and recommendations. 2.3 THE FIELD TEAM Each field team consists of 7 members (Rahman, 2016).The field team will be accompanied by an IP member (preferably the forestry graduate/diploma in forestry) while they are working in Chittagong Hill Tracts and Madhupur Tracts. The BFI unit will distribute the work of inventory to the field teams. The field team coordinators should select their camping sites in such a manner that maximum number of sample
FAO_6086-f.pdf | 10 | the QA/QC team would need to re-measure a third sub-plot and so on, until at least 15 trees have been re- | measured. It is important to remember that once the QA/QC team starts re-measuring a sub-plot, it has to | the QA/QC team would need to re-measure a third sub-plot and so on, until at least 15 trees have been re- measured. It is important to remember that once the QA/QC team starts re-measuring a sub-plot, it has to complete it. At least 7% of the plots are cold checked. Cold-check score sheet and reporting The cold-check process requires the data collected by the QA/QC crew to be checked against the data collected by the field team. The QA/QC team completes the check with a copy of the field team’s data in hand so they can directly cross check the results. Through this process, all the errors that have been identified by the QA/QC team have to be entered into the cold-check score sheet. The score sheet, once filled, automatically provides a QA/QC score which can be used to assess the work of the field crew. A score of 100% means that no errors have been found, scores smaller than 85% are considered unsatisfactory. A detailed description of the score sheet is provided in the appendix. Based on the information contained in the score sheet, the QA/QC team compiles a cold-check report which will contain the score, as calculated by the score sheet a summary of the inspections, including a list of all relevant errors that has been found, and all other comments and follow-up actions. The report will be submitted to the field crew for discussion and to the BFI unit. The QA/QC team cordinator is responsible for preparing cold-check score sheet and report. CHECKS FOR SOIL AND PLANT SPECIMEN SAMPLES Objective: To ensure that the soil samples and plant specimens are properly collected and labelled. Definition: The soil samples and plant specimen need to be propely collected and sent to the laboratory for analysis and identification on the latest two weeks after the field data coleciton. The BFI unit must be informed about the transfer of the samples in order to prevent any loss of field samples data for any reasons. Regarding the soil samples, two types of sample are collected in t
FAO_6086-f.pdf | 11 | FREQUENT TRANSFER OF FIELD DATA TO A CENTRAL LOCATION FOR BACK-UP | Objective: To prevent loss of data due to lost or damaged tablets or corrupted digital | FREQUENT TRANSFER OF FIELD DATA TO A CENTRAL LOCATION FOR BACK-UP Objective: To prevent loss of data due to lost or damaged tablets or corrupted digital files, or due to lost field forms. Definition: The data need to be transferred within one week to the BFI unit after the completion of each plot. This will help prevent loss of data for any unavoidable reasons, avoid re-measurement of plot and enable central staff to check the correctness of data on a regular basis. The soil and plant specimen samples need to be sent to the laboratory for analysis on the latest after two weeks after their collection. Once the lab technicians receive the samples, they will complete the QA/QC form for the soil and plant specimen collection. 3.4 AFTER THE FIELD WORK: CHECK FOR ERRORS IN THE OFFICE Objective: Despite all cautions it is likely that there might be some unexpected values in the field form recorded by the field crews. Such errors should be checked in the office to maintain quality of data. Definition: In the office, the BFI unit undertakes several data check to identify unexpected values (e.g., unreasonably large values of DBH, height, etc., or tree species being recorded in unexpected locations). These checks can be done using statistical software, such as R. The research officers, foresters currently working in the BFI Unit will be assigned to check and report such errors. Data quality control has to encompass also the results concerning soil organic carbon contents produced by the laboratory. 3.5 TRANSFER OF ALL DATA, EITHER BEFORE OR AFTER ERROR-CHECKING, TO A CENTRAL DATABASE Objective: All data should be transferred to a central data base after QC and error- checking for further use. Definition: Data received from QA/QC team in the field and checked for error in the office should be stored in a central data base. This data can be then used for further analysis and interpretation. 3.6 DOCUMENTATION All necessary documentation regarding QA/QC has to be archived in the R
FAO_6086-f.pdf | 2 | Quality Assurance and quality Control for the Bangladesh Forest | Inventory | Quality Assurance and quality Control for the Bangladesh Forest Inventory Published by Forest Department, Ministry of Environment and Forests, 2017. Contact: Forest Department Ministry of Environment and Forests Government of the People’s Republic of Bangladesh Bana Bhaban, Plot No- E-8, B-2 Agargaon, Sher-e-Bangla Nagar Dhaka-1207 info@bforest.gov.bd This effort is financially supported by United States Agency for International Development (USAID) with technical support from Food and Agriculture Organization of the United Nations (FAO). Contributors: Laskar Muqsudur Rahman1, Zaheer Iqbal2, Luca Birigazzi1, Hossain Mohammad Nishad2, Liam Costello1, Mahmood Hossain3, Matieu Henry1, Heather Hayden4, Frida Siddik1, Mariam Akhter1, Sourav Das5, Rashid Manzoor5, Rashed Jalal1, Md. Baktiar Nur Siddiqui2, Mohammad Main Uddin6, Khaled Misbazuzzaman6, , Mohammad Raqibul Hasan Siddique3, Md. Rakibul Hasan Mukul2, Falgoonee Kumar Mondal 1 1 Food and Agricultural Organization of the United Nations 2 Bangladesh Forest Department 3 Khulna University 4 US Forest Service 5 Shahjalal University of Science and Technology 6 Chittagong University Suggested Citation: BFD. 2016. Quality assurance and quality control for the Bangladesh Forest Inventory. Bangladesh Forest Department, Food and Agricultural Organization of the United Nations, Dhaka, Bangladesh. ISBN 978-984-34-2713-7 Disclaimer This report is designed to reflect the activities and progress related to the project GCP/GD/058/USAID “Strengthening National Forest Inventory and Satellite Forest Monitoring System in support of REDD+ in Bangladesh”. This report is not authoritative information sources – it does not reflect the official position of the supporting international agencies including USAID or FAO and should not be used for official purposes. Should readers find any errors in the document or would like to provide comments for improving its quality they are encouraged to contact one of above contacts. © 2017 Forest Departm
FAO_6086-f.pdf | 12 | 4 IMPROVEMENT PLAN | Improve | 4 IMPROVEMENT PLAN Improve Objective: Identification of the necessary actions to improve the next national forest inventory cycle Definition: To improve the quality of next inventory necessary actions Guide Learn needs to be taken. These may include improvement of sample design, prioritization of biophysical variables to meet the stakeholders’ requirement, and, regarding the QA/QC, implementation strategies for data collection, data collection process, identification of sources of errors and aptitude of data collector. The improvement plan will be developed by the BFI unit that aims to facilitate continual improvement of the Bangladesh Forest Inventory. It helps priorities improvement activities, adhere national forest inventory to national priorities and the internationally accepted principles meet the needs of policy-makers, researchers and the public and facilitate continual inventory improvement. Documentation of improvement plan helps guide the BFI unit to improve the quality of the national forest inventory for the next cycle. The improvements areas will mainly center around three issues: (1) identifying source of errors, (2) coordination between institutions especially for data collection, and (3) building capacity. 5 CONCLUSION Differences in measurements are only considered “errors” when they are greater than the tolerance set for the variable in question and beyond the compliance standard. Measurements of the QA/AC teams must be done very carefully to ensure that they are correct, before determining whether the field team’s measurements are incorrect. A minimum number of Hot and Cold checks should be done on every crew. A particular care should be given to the Cold Check evaluations, pointing out what the field crew should work on as well as pointing out positive aspects of their work. Before making a determination of right or wrong, consider the field crew’s notes and look at the situation from their perspective. The QA/QC procedure is crucial to ensure t
FAO_6086-f.pdf | 4 | LIST OF ACRONYMS | Acronyms | LIST OF ACRONYMS Acronyms Description ACF Assistant Conservator of Forest BFI Bangladesh Forest Inventory CWD Coarse Wood Debris DBH Diameter at Breast Height DCCF Deputy Chief Conservator of Forest DCF Deputy Conservator of Forest DWM Down Woody Material IP Indigenous people MQO Measurement Quality Objectives QA/QC Quality Assurance/Quality Control RP Reference Point SP Skilled Person TC Team Cordinator TE Team Expert 6

## Graph
File Name | Page Number | Graph Image | Graph Image Caption | Description

## Table-1
LIST OF ACRONYMS
Acronyms | Description
ACF | Assistant Conservator of Forest
BFI | Bangladesh Forest Inventory
CWD | Coarse Wood Debris
DBH | Diameter at Breast Height
DCCF | Deputy Chief Conservator of Forest
DCF | Deputy Conservator of Forest
DWM | Down Woody Material
IP | Indigenous people
MQO | Measurement Quality Objectives
QA/QC | Quality Assurance/Quality Control
RP | Reference Point
SP | Skilled Person
TC | Team Cordinator
TE | Team Expert